## Sheet1
Resource | Assignments for this week | Probable tasks for next week
Shadab | 1)Supporting Wells for splitting batch CSV to individual FIXMLs 2)Start work on moving from Hudson to Jenkins as our continuous build tool | 1) Continue with setting up Jenkins as the buid tool. 2) Start work on building Stored Proc End Point
Meenakshi | 1) Involved in MCH KT 2) Worked on DTCC Dissimination POC 3) Currently working on resolving Mail Component Issue for Wells | Work on the next roadmap item.
Nanjesh | Not available for this week. | Will start work on building the commnad line based installer.
Ritwik | 1) Work on Wells Issues 2) Working on Data Model and requirements for DTCC Data View 3) Continue Design discussions with Vance | 1) Code Review for Critical Components of Teevra Core (As per roadmap) 2) Finalize the process for integrating code from GitHub into svn
Saurabh | 1) HKFE testing with MS 2) Development plan for TSE and TFX can be prepared post translation of TSE and TFX docs. 3) Worked on queries from MS. | 1)Start on TSE and TFX design and development. 2)Prepare development schedule for TSE and TFX.
Manoj | 1) Worked on ASX issues and queries from MS reported by MS. | Start with TSE specs analysis (depends on translation)
Deepak | 1) Worked on LIFFE FIXML issue reported by MS. | Resolve the LIFFE FIXML issue and start with Euronext testing.
Pardha | 1) Working on TSE and TFX specs. 2) Working on OTC connectivity gateway. | Start with TSE BRD and mappings (depends on translation)
Suhas | Complete testing for JPMC POC on ICE Clear Europe. | Continue with same. Look into recovery issues.
Tanvir | On Leave | Start with TFX specs analysis(depends on translation)
Rachit | Test Work | Test Comment